{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["КС-2"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"КС-2","index":0,"n_rows":38,"n_cols":9,"rows_kept":38,"cut":false,"hidden":false,"merged":[[25,2,25,3],[23,2,23,3],[21,6,21,8],[21,5,22,5],[21,2,22,3],[7,0,7,4],[14,4,14,5],[28,2,28,3],[21,0,21,1],[34,7,34,8],[37,7,37,8],[37,4,37,5],[34,4,34,5],[8,0,8,7],[14,7,14,8],[15,4,15,5],[16,4,16,5],[21,4,22,4],[17,0,17,7]],"flags":["formulas_cached_only"]}
[{"$nulls":8},"Унифицированная форма № КС-2"]
[{"$nulls":8},"Утверждена постановлением Госкомстата России от 11.11.99 № 100"]
[{"$nulls":8},"код"]
[{"$nulls":6},"Форма","по ОКУД",322005]
["Инвестор",{"$nulls":6},"по ОКПО"]
["Заказчик (Генподрядчик):   ООО \"С\"",{"$nulls":6},"по ОКПО"]
["Подрядчик (Субподрядчик):   ООО \"Л\"",{"$nulls":6},"по ОКПО"]
["Стройка:"]
["Объект:   "]
[{"$nulls":7},"Вид деятельности по ОКПД"]
[{"$nulls":6},"Договор подряда (контракт)","номер"]
[{"$nulls":7},"дата","2012-08-24"]
[{"$nulls":7},"Вид операции"]
[]
[null,null,null,"Номер ","Дата ",null,null,"Отчетный период"]
[null,null,null,"документа","составления",null,null,"с","по"]
[null,null,"А К Т",1,"2012-09-28",null,null,"2012-08-24","2012-08-28"]
["о приемке выполненных работ"]
[]
["Сметная (договорная) стоимость в соответствии с договором подряда (субподряда)",{"$nulls":6},153970,"руб."]
[]
["Номер",null,"Наименование работ",null,"Номер единичной расценки","Ед. изм.","Выполнено работ"]
["по порядку","позиции по смете",{"$nulls":4},"Кол-во","Цена за ед., руб.","Стоимость, руб."]
[1,2,3,null,4,5,6,7,8]
[null,null,"Раздел 1. ПД1"]
[1,null,"Огнезащитное покрытие несущих металлоконструкций комплекной огнезащитой El 150 с пределом огнестойкости 2,5 часа",null,null,"100 м2 обрабатываемой поверхности",0.78,530,41340]
[2,null,"Огнезащитный состав с прделом огнестойкости 2,5 часа",null,null,"м2",78,360,28080]
[null,null,"Раздел 3. ВД1"]
[3,null,"Огнезащитное покрытие несущих металлоконструкций комплекной огнезащитой El 150 с пределом огнестойкости 2,5 часа",null,null,"100 м2 обрабатываемой поверхности",0.95,530,50350]
[4,null,"Огнезащитный состав с прделом огнестойкости 2,5 часа",null,null,"м2",95,360,34200]
[{"$nulls":5},"Итого:",null,1420,153970]
[]
[]
[null,"Сдал","Директор",{"$nulls":4},"Шиков А.А."]
[null,null,"должность визирующего лица от Подрядчика (Субподрядчика)",null,"подпись",null,null,"расшифровка фамилии"]
[]
[null,"Принял","Директор",{"$nulls":4},"Шаймуратов Е.Р."]
[null,null,"должность визирующего лица от Заказчика (Генподрядчика)",null,"подпись",null,null,"расшифровка фамилии"]